## Sheet1
Task Name | Start Date | End Date
Create and establish shared sites | 2023-01-02 | 2023-01-05
establish project requirements | 2023-01-02 | 2023-01-10
Research MSP430 | 2023-01-02 | 2023-01-23
proposal draft checkin (Acken) | 2023-01-02 | 2023-01-23
proposal draft checkin (Greenberg) | 2023-01-23 | 2023-01-24
PM2.5 Sensor Selection | 2023-01-23 | 2023-02-18
CO2 Sensor Selection | 2023-01-23 | 2023-02-18
Develope code for CO2 sensor | 2023-01-27 | 2023-03-29
proposal draft checkin (Burnett) | 2023-01-27 | 2023-02-26
BOM | 2023-01-27 | 2023-02-25
Order Parts | 2023-01-27 | 2023-02-20
Develope code for PM2.5 sensor | 2023-01-27 | 2023-03-29
Develope code for annomometer | 2023-01-27 | 2023-03-29
research and debug smart mesh | 2023-01-27 | 2023-03-29
initial hardware prototype | 2023-02-09 | 2023-04-10
mesh sensor codes | 2023-02-26 | 2023-04-03
Task Name | Start Date | Task Duration | assigned to:
Create and establish shared sites | 44928 | 3 | Adam, Brandon, Manuel, Mercedes
establish project requirements | 44928 | 8 | Adam, Brandon, Manuel, Mercedes
Research MSP430 | 44928 | 21 | Adam, Brandon, Manuel, Mercedes
proposal draft checkin (Acken) | 44928 | 21 | Adam, Brandon, Manuel, Mercedes
proposal draft checkin (Greenberg) | 44949 | 1 | Adam, Brandon, Manuel, Mercedes
PM2.5 Sensor Selection | 44949 | 26 | Mercedes
CO2 Sensor Selection | 44949 | 26 | Adam
Develope code for CO2 sensor | 44953 | 61 | Adam
proposal draft checkin (Burnett) | 44953 | 30 | Adam, Brandon, Manuel, Mercedes
BOM | 44953 | 29 | Adam, Brandon, Manuel, Mercedes
Order Parts | 44953 | 24 | Adam, Brandon, Manuel, Mercedes
Develope code for PM2.5 sensor | 44953 | 61 | Mercedes
Develope code for annonemer | 44953 | 61 | Brandon
research and debug smart mesh | 44953 | 61 | Manuel
initial hardware prototype | 44966 | 60 | Adam, Brandon, Manuel, Mercedes
mesh sensor codes | 44983 | 36 | Adam, Brandon, Manuel, Mercedes
Task Name | start date | end date
Develope code for CO2 sensor | 2023-03-27 | 2023-03-29
Develope code for PM2.5 sensor | 2023-03-27 | 2023-03-29
Develope code for annomometer | 2023-03-27 | 2023-03-29
Research and debug smart mesh | 2023-03-27 | 2023-03-29
initial hardware prototype | 2023-03-27 | 2023-04-10
mesh sensor codes | 2023-03-27 | 2023-04-03
Task Name | start date | duration
Develope code for CO2 sensor | 45012 | 2
Develope code for PM2.5 sensor | 45012 | 2
Develope code for annomometer | 45012 | 2
Research and debug smart mesh | 45012 | 2
initial hardware prototype | 45012 | 14
mesh sensor codes | 45012 | 7
Task Name | Start date | End date
Begin software mesh | 2023-03-25 | 2023-04-05
Software Optimization | 2023-04-01 | 2023-05-01
PCB Schematic | 2023-04-19 | 2023-05-08
Enclosure Build | 2023-04-24 | 2023-05-29
Testing and debugging/ troubleshooting code | 2023-05-01 | 2023-05-31
PCB Build | 2023-05-08 | 2023-05-20
final doccumentation | 2023-06-01 | 2023-06-16
Capstone poster | 2023-06-01 | 2023-06-16
Final project report | 2023-06-01 | 2023-06-16
Task Name | Start date | Duration
begin software mesh | 45010 | 11
Software Optimization | 45017 | 30
PCB Schematic | 45035 | 19
Enclosure Build | 45040 | 35
Testing and debugging/ troubleshooting code | 45047 | 30
PCB Build | 45054 | 12
final doccumentation | 45078 | 15
Capstone poster | 45078 | 15
Final project report | 45078 | 15